## Project Timeline
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Mower-WC 20-1 | [6 empty] | SIMPLE GANTT CHART by Vertex42.com
Enter Company Name in cell B2. | Company Name | [6 empty] | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Project Lead | Project Start: |  |  | 2020-12-26
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  |  | 1 |  |  | 2020-12-21 | [6 empty] | 2020-12-28 | [6 empty] | 2021-01-04 | [6 empty] | 2021-01-11 | [6 empty] | 2021-01-18 | [6 empty] | 2021-01-25 | [6 empty] | 2021-02-01 | [6 empty] | 2021-02-08
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2020-12-21 to 2021-02-14
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | REMARKS | PROGRESS | START | END | DAYS | bar: 2020-12-21 to 2021-02-14
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Project Kick-Off Meeting | bar: 2020-12-26
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Give all project members an overview of the project | Muhammad Affandi Bin Mansor | As on 26/12: i) Change Gantt chart, use the template | 100% | 2020-12-26 | 2020-12-26 | 1
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Product design review | bar: 2020-12-26 to 2020-12-27
| Review and discuss the functionalities of: i) Chasis ii) Connecting arm iii) Cutter head iv) Remote control | Muhammad Affandi Bin Mansor | As on 18/12: i) Still no final decision on the connecting mechanism ii) The cutting mechanism is yet to decide As on 26/12: i) Cutting mechanism is decided = rotary | 100% | 2020-12-26 | 2020-12-27 | 2
Sample phase title block | Change of the product design | bar: 2020-12-27 to 2020-12-28
| Research the possible solutions for outcomes/problems from the product's design review | Muhammad Affandi Bin Mansor | As on 26/12: i) Remote controller: Added a new function - Emergency stop button) ii) Connecting arm: Simplify lower vertical pole connection by using only one threaded beam iii) Attachment from chasis to the connecting arm still open, basic idea is using concept like gopro mounting or L-joint iv) Blade diameter: 330mm As on 27/12: i) Connection arm will be attached to the chasis by using a L-joint ii) Size of the cutter diameter is reduced to 160mm(including blades) | 100% | 2020-12-27 | 2020-12-28 | 2
3D Model construction | bar: 2020-12-27 to 2020-12-29
| Defining all components need to be assembled on the chassis | Affandi Hakim Acap | As on 28/12: i) 3D Model needs to tweaked on suspension and back wheel ii) 3D drawing iii) Shopping on hold As on 31/12: i) Needs to buy extra UNO (and NANO) done-9/1/2021 ii) Wire for min 5Amp and 3Amp (neutral and live) done-9/1/2021 iii) PCB 40pcs done-9/1/2021 iv) PCB terminal (screw mount) done-9/1/2021 v) Soldering kit and paste done-9/1/2021 vi) USB for arduino done-9/1/2021 As on 10/1: i) 3D-Modelling is already completed ii) Refinement still in process e.g. Screw sizes, hole diameter etc. (open) | 90% | 2020-12-27 | 2020-12-27 | 1
| Dimensioning all mechanical components | Affandi Hakim |  | 90% | 2020-12-27 | 2020-12-28 | 2
| Sketch 3D model of the mechanical components based on 2D sketch | Affandi Hakim |  | 100% | 2020-12-27 | 2020-12-28 | 2
| Buy extra mechanical and electronical parts needed (e.g. metal plate, metal bar, L/U-joints, screws etc.) | Affandi Hakim Acap |  | 100% | 2020-12-28 | 2020-12-29 | 2
Designing the electrical circuit | bar: 2020-12-27 to 2020-12-29
| List all the current, voltage and power drawn by all components | Acap Affandi Hakim | As on 27/12: i) The voltage needed by all users have been listed down in a Schematic Diagram ppt As on 28/12: i) Current draw from motors needs to be checked on multimeter ii) 2 Circuits have been drawn (Arduino circuit and Voltage divider for simulation). Circuits still need to be validated As on 31/12: i) Electrical circuits need to be adjusted As on 10/1: i) Electrical circuits need to be adjusted (voltage supply tp chassis motors will be increased from 8V to 12V) (open) ii) So far for joystick control operating mode the electrical circuit is completed. iii) Inbetriebnahme (soldering on pcb) (open) | 80% | 2020-12-27 | 2020-12-27 | 1
| Calculate the size of resistor, capacitor etc. required | Acap Affandi |  | 80% | 2020-12-27 | 2020-12-28 | 2
| Sketch the electrical circuit in software | Acap Hakim Affandi |  | 80% | 2020-12-28 | 2020-12-29 | 2
Microcontroller programming & testing | bar: 2020-12-29 to 2020-12-30
| i) Look for open source codes based on the functionalities of the robot ii) Amend the codes to suit the purposes of this project | Affandi Hakim Acap | As on 31/12: i) Hakim OLED - 10% youtube learning ii) Static testing for all motors has been done iii) Static testing all components combined needs to be done (open) As on 2/1: i) Static test for all motors has been done ii) A program to control the chasis movement using joystick and to activate the cutter motor using a switch has been written. ii) Motors on chassis run on different speeds by a same current and voltage supplied. Calibration needed (done. See done-3 below) iii) Idea to create an algorithm that can smooth the turning process based on the position of joystick (open-1) As on 4/1: i) Measure rotational speed by using ultrasonic sensor in order to calibrate the motors. Setup a test bench. (open-2) As on 5/1: i) Voltage and current for M1 and M2 have been measured a. Forward and reverse movement b. Voltage is varied using PWM from 6-12V ii) Both output terminals of L298N motor driver delivered different voltage to the chassis motors iii) Troubleshoot: a. Different in voltage output from both L298N outputs(open-3. See done-3 below) b. Different between voltage-IST and voltage-SOLL on the L298N outputs (open-4. See done-4 below) As on 6/1: i) For troubleshoot i.a. --> Arduino forum suggests that pin 3 and 4 have different PWM signal's frequency. This accounts for the different voltage output on both L298N output terminals. (done-3) ii) Link to forum above: https://forum.arduino.cc/index.php?topic=324690.0 As on 8/1: i) fPWM is responsible for the amount of current flows into the motors. Low fPWM accounted for high current flow in the motor --> V=IR is high (done-4) ii) see further explanation in Mower-WC20-1 Notebook -->Test--> Result-calibration straight maneuver (2nd Excel worksheet) As on 10/1: i) Fendi: a. Algorithm for turning maneuver still (see done-5) b. Measure rotational speed for both motors using ultrasonic sensors (open) c. To further investigate the effect of increasing fPWM on the voltage ouputs of the motor driver. --> increase fPWM above 980Hz by using specific library in arduino. ii) Hakim a. Still learning to create different pages for menu according to operating modus (e.g. cutter motor, chassis motor, battery status) (open) b. Learning an overview about C++ and OOP (open) c. First step --> interaction OLED and pushbutton (open) iii) Acap a. UNO & mega communication through nRF24L01 is completed b. Chassis motors(M1&M2) has been tested and its ok! c. Toggle switch for cutter motor also has been connected and ist ok! (represented with LED so far). d. Communication test with actual motor cutter still pending (open) As on 19/3: i) Fendi: a. Turning maneuver is completed but needs minor changes (done-5) b. Radio communication between controller and chassis has been programmed c. Testing radio communication for controller/chassis (open) | 80% | 2020-12-29 | 2020-12-30 | 2
| Testing and calculate the current, voltage and power supplied to all components | Affandi Hakim Acap |  | 60% | 2020-12-29 | 2020-12-30 | 2
Hardware construction | bar: 2020-12-30 to 2020-12-31
| Do all the handworks i) Cutting ii) Drilling | Affandi Hakim | As on 31/12: i) Put on hold because components still cannot be bought As on 19/3: i) Platform extension on the chassis is completed ii) Cutter head construction is completed iii) Protecting cover for cutter blades is still open | 90% | 2020-12-30 | 2020-12-31 | 2
Components assembling | bar: 2020-12-31 to 2021-01-01
| Assemble all the mechanical parts together | Affandi Hakim | As on 19/3: i) Assembly of cutter head and platform extension on the chassis is completed | 90% | 2020-12-31 | 2020-12-31 | 1
| Installing all the electrical components on the chassis | Affandi Hakim Acap |  | 0% | 2021-01-01 | 2021-01-01 | 1
Product testing | bar: 2021-01-01 to 2021-01-02
| Start the field test of the complete product | Affandi Hakim Acap |  |  | 2021-01-01 | 2021-01-02 | 2
| Evaluate product's performance and energy usage | Affandi Hakim Acap |  |  | 2021-01-02 | 2021-01-03
Project revision | bar: 2021-01-03
This is an empty row | Discuss among project members if the project's purposes and outcomes are fulfilled/achieved | Affandi Hakim Acap |  |  | 2021-01-03 | 2021-01-03 | 1
| What constructive changes can be done in order to deliver a better product (In terms of project management, technical aspects, product functionalities etc.) | Affandi Hakim Acap |  |  | 2021-01-03 | 2021-01-03 | 1
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one

## Project Milestone
Date | Milestone | Height | Helper Column
2020-12-26 | Project Kickoff | 0.3 | 0
2020-12-27 | Look out and testing the library for radio communication | 0.4 | 0
2020-12-28 | Add joystick and switch functionalities to the code | 0.5 | 0
2020-12-29 | Testing output on the LEDs and motors | 0.6 | 0
2021-01-05 | Designing the software architecture for OOP | 0.7 | 0
2021-01-16 | Start of Implementation of the software architecture | 0.8 | 0
2021-01-23 | Release the joystick, switch and LED source code | 0.35 | 0
2021-02-06 | Release the cutter and chassis motor source code | 0.4 | 0
2021-03-06 | Release the sketch for controller | 0.4 | 0
2021-03-20 | Release the sketch for chassis | 0.45 | 0
2021-03-23 | Add the radio communication to the chassis and controller | 0.5 | 0
2021-03-28 | Test and validate the sketches for chassis and controller | 0.6 | 0
2021-04-04 | End of Implementation of the software architecture | 0.8 | 0
2021-04-25 | Project End | 0.5 | 0
TIMELINE OF MILESTONES
CLICK TO VIEW THIS TUTORIAL ONLINE >>
SUBSCRIBE TO THE NEWSLETTER >>
VIEW OUR ONLINE EXCEL COURSES >>
LISTEN TO MY EXCEL PODCAST SHOW >>

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.

## Action List
Action | Details | Remarks | Status
Project Kick-Off meeting | i) Give all project members an overview of the project -Project's purposes and outcomes -Timeline -Actual product design | As on 26/12: i) Change Gantt chart, use the template | done
Product design review | - Review and discuss the listed functionalities of: i) Chassis ii) Connecting arm iii) Cutter head iv) Remote controller | As on 18/12: i) Still no final decision on the connecting mechanism ii) The cutting mechanism is yet to decide As on 26/12: i) Cutting mechanism is decided = rotary | done
Change of the product design | i) Research the possible solutions for outcomes/problems from the Product design review's phase | As on 26/12: i) Remote controller: Added a new function - Emergency stop button) ii) Connecting arm: Simplify lower vertical pole connection by using only one threaded beam iii) Attachment from chasis to the connecting arm still open, basic idea is using concept like gopro mounting or L-joint iv) Blade diameter: 330mm As on 27/12: i) Connection arm will be attached to the chasis by using a L-joint ii) Size of the cutter diameter is reduced to 160mm(including blades) | done
3D Model construction | i) Defining all components need to be assembled on the chassis ii) Dimensioning all the mechanical components iii) Sketch the 3D model of the mechanical components in Creo Parametric based on the 2D sketch iv) Buy extra mechanical parts needed (e.g. metal plate, metal bar, L/U-joints, screws etc.) | As on 28/12: i) 3D Model needs to tweaked on suspension and back wheel ii) 3D drawing iii) Shopping on hold | open
Designing the electrical circuit | i) List all the current, voltage and power drawn by all components ii) Calculate the size of resistor, capacitor etc. required iii) Sketch the electrical circuit in software | As on 27/12: i) The voltage needed by all users have been listed down in a Schematic Diagram ppt As on 28/12: i) Current draw from motors needs to be checked on multimeter ii) 2 Circuits have been drawn (Arduino circuit and Voltage divider for simulation). Circuits still need to be validated | open
Microcontroller programming & testing | i) Look for open source codes based on the functionalities of the robot ii) Amend the codes to suit the purposes of this project iii) Testing and calculate the current, voltage and power supplied to all components
Hardware construction | i) Do all the handworks ii) Complete or extend the available chassis in order to place all the electrical components ii) Construction of the connecting arm and cutter head
Components assembling | i) Assemble all the mechanical parts together ii) Installing all the electrical components on the chassis
Product testing | i) Start the field test of the complete product ii) Evaluate product's performance and energy usage
Project revision | i) End phase of the project ii) Discuss among project members if the project's purposes and outcomes are fulfilled/achieved iii) What constructive changes can be done in order to deliver a better product (In terms of project management, technical aspects, product functionalities etc.)